## Feedback Responses 3.24.23
Feedback on the EI-Hub System
The Feedback on the EI-Hub System log is a representation of the feedback received from end-users on their experience with the EI-Hub. The information in the log was received through a variety of mechanisms, such as the Sandbox Feedback Form, EI-Hub email, Help Desk tickets, etc. Feedback is reviewed regularly by the EI-Hub Project Team and this document is updated on a bi-weekly (every other week) basis. You will be able to see what your peers are saying about the EI-Hub, what the EI-Hub's Project Team's response is to the feedback, and any applicable training resources.
Status Descriptions
4 | Completed / Implemented |  |  | Have feedback you want to share? Not seeing a topic below? |  | Still Have Questions or Need Help?
3 | In Progress |  |  | Please click the link below to share your comments |  | Please contact the PCG Call Center for assistance at:
2 | Delayed / Discontinued |  |  | Click Here |  | Tel#: (866) 315-3747
1 | Not Started |  |  |  |  | Email: NYEITraining@pcgus.com
Status | Last Updated | Topic | EI-Hub System Category | Details | Response | Applicable Resources | Screenshots
4 | 2024-09-27 | Feedback Survey | EI-Hub | Users suggest that specific concerns are not addressed in the feedback log | The EI-Hub project team reviews every comment submitted through the feedback form and provides a response. If you need further assistance on a specific topic, please contact the PCG Call Center for further support.
1 | 2024-09-27 | Dashboards | Case Management | Users suggested an enhancement to the dashboard to more easily identify a child’s current stage within the EIP. | Thank you for this feedback! We have shared this recommendation with the development team for consideration as a future system enhancement.
4 | 2024-09-27 | IFSP | Case Management | Users suggested a system enhancement to the EIO/D approval column within the IFSP Services Grid. | Currently in the Sandbox, the IFSP Services Grid displays all services associated with a specific IFSP and includes a column for EIO/D approval. By default, this column displays all values as 'rejected' in the grid view if no action has been taken by the EIO/D to approve or reject. At go-live, this column will remain blank until the EIO/D takes action on the service.
4 | 2024-09-23 | Evaluations | Case Management | Users inquired about the process for adding multiple evaluators to the IFSP Teams panel. | In the IFSP Teams panel, users have two options for adding evaluators as team members: 'Evaluator' or 'Other'. Choosing 'Evaluator' displays the primary evaluator only. To include a secondary evaluator, select 'Other,' and enter their name in the designated fields, and specify their role or purpose for attending the meeting in the notes section (e.g., 'Second Evaluator').
4 | 2024-09-23 | Sandbox Functionality | EI-Hub Sandbox | Users have reported difficulties using the Sandbox, including the inability to view children following the recent enhancement. | There are several possible reasons why a user may be unable to view children in the Sandbox. For assistance, please contact the PCG Call Center. There are dedicated agents available Monday through Friday from 7:00am to 7:00pm to assist you.
3 | 2024-09-23 | IFSP | Case Management | Users inquired how IFSP meeting minutes can be included as part of the printed IFSP | The Meeting Minutes field in the EI-Hub is designated for internal notes only and will not be included in the printed IFSP. If a note from the IFSP meeting needs to be included in the printed IFSP, it can be documented in the "Level of Development" panel. This feedback has been shared with the development team for consideration as a future system enhancement.
3 | 2024-09-23 | IFSP | Case Management | User questioned if inactive services copy from the previous IFSP to the new one when an IFSP is amended. | In the EI-Hub, an IFSP can be approved without assigning a provider to a service. That service will remain inactive until a provider is added to and accepts the SA. All inactive SAs will be carried over to an IFSP when it is copied. For example, when you make an amendment, extension, 6-month review, etc. This feature is coming to the Sandbox environment and will be available at go-live.
4 | 2024-09-16 | Training Resources | EI-Hub | Users inquired about the planning process for the EI-Hub training. | The most recent in-person training sessions (July – August 2024) were developed in collaboration with NYSACHO. Feedback from the field indicated a need for additional in-person training across the state. Both NYSACHO and county representatives contributed to shaping the training curriculum and logistics including available dates and locations. Additionally, the training team incorporated feedback from previous sessions and Call Center inquiries into the curriculum design. Trainers have actively sought and used user feedback throughout the training process, making adjustments to better address the needs of the field.
4 | 2024-09-16 | Dashboards | Case Management | Users have asked for additional details about the new "Retrieve" button on the Children Assigned to Caseload dashboard. | In May 2024, a “Retrieve” button was added to the Children Assigned to Caseload dashboard. Previously, users reported having to wait for the dashboard to populate before navigating through the system. The “Retrieve” button now allows users to generate this information on demand. This also allows users going into Case Management for other reasons, such as retrieving a report or performing a child search, to go directly to those areas of the system.
1 | 2024-09-16 | Sandbox Setup | EI-Hub Sandbox | Users have inquired about the data available in the enhanced Sandbox and whether it is migrated from NYEIS. | The enhanced Sandbox uses data sourced from NYEIS, but the child data has been intentionally altered and manipulated. The child data in the enhanced Sandbox should not be considered as migrated NYEIS data. Users should not attempt to compare child data in the Sandbox with child data in NYEIS.
4 | 2024-09-16 | Service Authorizations | Case Management | Users questioned the meaning of 'active' status for services listed in the Services tab. | The Service Status column in the Services tab within case management reflects the approval status of a Service Authorization (SA). If an SA was approved at any point, the column will display 'Active.' This applies to migrated NYEIS data where the SA status was Active, Approved, Extended, Suspended, or Closed. This logic also applies to any new SAs entered in the EI-Hub. The column will display 'Inactive' only if the SA has never been approved. In the EI-Hub Service Logging component, 'Active' refers to SAs within the authorized start and end dates, while 'Inactive' indicates SAs outside the authorized timeframe. Users can still bill against an 'Inactive' SA if the service delivery date falls within the authorized timeframe. For more information, please reference the appropriate job aids.
4 | 2024-09-16 | General System Functionality | EI-Hub | Users inquired about the process for sending tasks between users in the EI-Hub. | The EI-Hub uses dashboards which replace the inbox/work queues and tasks currently used in NYEIS. Dashboards will allow users to track which tasks are outstanding, coming due, or past due. Users are encouraged to use the Sandbox to become familiar with the dashboards and learn how to manage their work effectively. The EI-Hub does include a task board; using task messages is optional and can be decided by each entity. If you use the task board and it appears distorted, try adjusting your browser settings.
4 | 2024-09-16 | Child Demographics | Case Management | Users suggested the insurance number be required in the Ins Info Tab when a user selects that the child has insurance. | The insurance policy number is not a required field; users can enter information as it becomes available. If a family indicates they have insurance but does not have the policy details on hand, you can document the insurance status and return later to add the policy number.
1 | 2024-09-16 | General System Functionality | Case Management | Users suggested a system enhancement that would prevent users from being re-directed back to the top (first) panel after entering data in certain areas of the system. | Thank you for this feedback! We have shared this recommendation with the development team for consideration as a future system enhancement.
1 | 2024-09-16 | General System Functionality | Case Management | Users have reported that not all required fields are marked with an asterisk. | This is a known issue in the EI-Hub. Required fields in the EI-Hub will have an asterisk and/or users will receive a notification when saving if a required field is not completed. We have shared this recommendation with the development team for consideration as a future system update.
4 | 2024-08-26 | Sandbox Setup | EI-Hub | Users questioned how user roles and access to the system modules are set up in the enhanced sandbox environment. | The Sandbox is a practice environment where users can familiarize themselves with the EI-Hub. On July 10th, an enhancement was made to the Sandbox to include authentic county, provider, and therapist data migrated from NYEIS. Users with an active NYEIS account were pre-assigned 1 user role in the EI Hub Case Management module. The assigned user role in the enhanced Sandbox environment reflects the role users will have in the EI Hub Case Management module when the EI-Hub formally launches. It's important to note that while the Sandbox provides users with an experience similar to the live system, it is not the live system. When the EI-Hub officially launches in October 2024, users will have only one pre-assigned role. Data and user role setup in the Sandbox do not carry over to the live system. The Role Administrator for each entity will be responsible for assigning any additional roles and granting access to other modules (Service Logging & Billing) in the system.
4 | 2024-08-26 | General System Functionality | EI-Hub | Users inquired whether the system was developed by experienced EI staff. | The EI-Hub was designed by a team that included subject matter experts in Early Intervention. Throughout the development process, suggestions from stakeholders in the field were incorporated into the system’s design. Additionally, the EI-Hub is configurable and will be updated as necessary throughout its lifecycle.
4 | 2024-08-26 | General System Functionality | Case Management | Users have expressed concerns about the amount of scrolling needed to view information in the grids | Users can change the screen size by manually adjusting the zoom settings in their browser. The amount of scrolling will vary based on individual browser settings. Helpful hint: arrows in the top-right corner of the grids to expand their size and minimize scrolling. Refer to the screenshot for an example. In the instances when an Excel button is available, users can also export the information to view and sort the data.
4 | 2024-08-26 | Transition | EI-Hub | Users questioned whether the implementation of the EI-Hub is also changing Early Intervention Program (EIP) policies and procedures. | The EI-Hub was designed to meet the requirements of the EIP and is not changing EIP policies and procedures. Counties and providers may need to look at the EI-Hub workflow and consider if internal processes need modifications.
4 | 2024-08-26 | Training Resources | EI-Hub | Users have shared feedback suggesting that they find the training materials confusing. | Training resources are available in multiple different formats and modalities, to address a variety of learning styles and needs. This includes, but is not limited to, job aids for key functions, micro e-learning videos for commonly requested training scenarios, and a comprehensive workflow resource guide offering step-by-step instruction. Training options have also included in-person sessions across multiple regions, live/recorded virtual training accessible from any location, and office hours for 1:1 support. For an overview on the available training resources on the EI-Hub, please reference the LMS Item Index.
4 | 2024-08-26 | EIO/D / SC Assignments | Case Management | Users questioned if the start date on the Teams tab could be backdated for EIO/Ds and ISCs. | Users can enter the appropriate start date that occurred in the past (“backdate”) on the Service Authorization for Initial Service Coordination, which would allow them to bill for activities that occurred before the child was entered into the system and the ISC was granted access to the record through the Teams tab. The Teams tab grants an EIO/D or SC access to a child's record within the EI-Hub. Start dates in this section cannot be backdated, as access cannot be applied retroactively. This panel is not connected to billing.
4 | 2024-08-26 | Service Authorizations | Case Management | Users recommended enhancing the assignment acceptance process by including additional details about the service authorization. | New assignment requests will appear in the agency’s ‘Children Assigned to Caseload’ dashboard. Under the ‘Action’ column, an ‘Accept Assignment’ button will appear. A pop-up will appear and display the type of service and date range. BEI/PCG are considering other updates to the acceptance screen. Any changes would be implemented post go-live. A best practice when assigning a provider for a service is to contact the agency to see if they have capacity of the child. In that discussion, counties should share the frequency and duration of the needed service. When the provider receives the request to accept the service, they would be aware of request.
4 | 2024-08-19 | Service Authorizations | Case Management | Users inquired how to properly document changes in Service Authorization (SA) numbers on telehealth consent forms | If the Service Authorization (SA) has been changed due to an amendment of the IFSP, and no changes were made to that individual service (e.g., frequency, duration, etc.), then a new Telehealth Consent Form would not be needed for that service; however, the new SA# will have to be tracked on the Telehealth Consent Form. The Telehealth Consent Form is currently being updated and will be distributed to the field prior to the launch of the EI-Hub.
4 | 2024-08-19 | Service Authorizations | Case Management | Users questioned how to enter co-visits when there are more than 2 Qualified Professionals (QP). | Early Intervention guidance allows for more than 2 QPs to be included in a co-visit. Users should document all QPs participating in the co-visit in the one of the ‘Level of Development’ (5 developmental areas) section of the IFSP. When drafting the IFSP, users will need to indicate that co-visits are needed when creating the Service Authorizations (SA). Separate SAs are required for all individuals that will be providing services to the child. While the Service Details panel only has the option to add one additional QP with the co-visit section, it does not prevent multiple QPs from being involved. As long as each QP has their own SA with one other QP listed, the co-visits will be approved with the SA and will pass billing validations.
4 | 2024-08-19 | Service Authorizations | Case Management | Users questioned if a prescription necessary in the EI-Hub for services that do not typically require one according to program guidelines? | The EI-Hub operates in compliance with the Bureau of Early Intervention OPRA guidance, meaning that EI Providers are not obliged to furnish a medical prescription for services that do not require a medical prescription, such as special instruction, group developmental service, service coordination, etc. Providers will need to complete the "Scripts, Orders, Recommendations, and Referrals” panel for each Service. This panel does not require a medical prescription for all services but does require a referring NPI for each Service Authorization, which for certain services, may be the NPI of the billing provider. Only services such as OT, PT and Nursing require a medical prescription. As long as the Billing Provider is enrolled in Medicaid, it does not have to be OPRA enrolled. The NPI number entered in this panel as the "prescriber" must match the referring NPI number listed on the claim to prevent claim rejection during edits/validations. This billing procedure aligns with current practices and adheres to existing guidance. This verification is done at the claim level in NYEIS; with the EI-Hub it is now at the service authorization and claim level. It's important to note that the billing agency may be considered the "referring provider" consistent with DOH policy since 2015.
3 | 2024-08-19 | Training Resources | Learning Management System | Users shared a suggestion for a training session that is role-specific and step-by-step, covering the process from referral to writing an IFSP. | Good news, there is a resource available on the Learning Management System (LMS) called the Workflow Resource Guide. This guide provides the who, what, where, when, and how to navigate a child through the Early Intervention Program using the EI-Hub. The guide is still in development, but sections from referral to eligibility are available right now. Additionally, there are many resources available on the Learning Management System (LMS) to support users in learning the EI-Hub. Visit the LMS to view available job aids, e-learning modules, previously recorded webinars and more. If you are looking to see what resources are available on a specific topic area, please reference the LMS Item Index.
4 | 2024-08-19 | IFSP | Case Management | Users noted that having auto-populated end dates for an IFSP would be beneficial. | During the development of the EI-Hub, the decision was made to not auto-populate end dates for initial IFSPs to provide flexibility to accommodate special circumstances. When users are creating a new IFSP, they will have to manually determine the end date. However, any copy of that IFSP will automatically calculate the next 6-month period from the end date of the original IFSP. A helpful hint, users can use an online date calculator to help with generating end dates.
4 | 2024-08-19 | General System Functionality | Case Management | Users reported concerns with the EI-Hub's system setup resulting in cumbersome data entry. | As with any change, adjusting to a new system is difficult. The EI-Hub Project Team acknowledges that there is a significant data entry requirement for users in the early stages of a child's time in EI. There are some benefits to this data entry including less data entry downstream as data carries through the system and more robust reporting capabilities. As users experience the system to administer the program, we are hopeful the usefulness of this upfront data entry will become more pronounced and time spent entering data will decrease.
3 | 2024-07-12 | Exit / Close | Case Management | Users have suggested that having a list of closure reason definitions would be helpful for the transition from NYEIS to the EI-Hub. | The Bureau is currently compiling a list of closure reasons and their definitions. A crosswalk of the EI-Hub values for case closures is in development. This resource will be available to users at the launch of the EI-Hub.
4 | 2024-07-12 | Dashboards | Case Management | Users requested a way to sort their Children Assigned to Caseload dashboard to identify child that require action. | At go-live and currently accessible in the Sandbox environment, a new column titled "Action Needed" was added to the Children Assigned to Caseload dashboard. This column serves to indicate whether any action is required in the Action column. It will provide a yes or no response and can be filtered to prioritize items needing attention. If the response is "Yes," an "Accept Assignment" or “Agency Assignment” option will be available in the Action column. If the response is "No," no action is required, and an "Edit" button will display in the Action column.
4 | 2024-07-03 | Sandbox Setup | EI-Hub Sandbox | Users shared that they do not have any components configured to their Sandbox account. | Thank you for providing your feedback. To access the components in the Sandbox, general users should reach out to their entity's Role Administrator. Role Administrators are responsible for managing user accounts for their respective entities. If you happen to be the Role Administrator for your entity, you can request Sandbox access by completing the Role Administrator Request form.
4 | 2024-07-03 | General System Functionality | EI-Hub | Users requested guidance on how to print information from a child's information from the EI-Hub for record retention purposes. | In the EI-Hub, the IFSP section includes a print option that consolidates identified panels within the IFSP tab into a single document. This is the only section of the system that compiles information from multiple panels. However, every panel within the system can be printed using a print screen option from your web browser. The EI-Hub data system is not meant to be used as the total repository for child records and is not an electronic record system. Therefore, documentation stored in the EI-Hub will not replace the paper record-keeping requirements or change the record-keeping responsibilities of early intervention providers, service coordinators, and municipalities that are outlined in regulation and in guidance. For more information about record retention, please visit Early Intervention Program Regulations Section 69-4.26(b) at https://regs.health.ny.gov/content/section-69-426-content-and-retention-child-records.
4 | 2024-07-03 | IFSP | Case Management | Users requested guidance on how to track which SAs have been approved during the IFSP approval process. | Each service within the IFSP needs to be approved individually. The Authorization Number and Service Status columns in the IFSP Services Grid will update once the IFSP has been approved and accepted by the provider. The IFSP Services Grid does not have a column or indicator to inform which services have already been approved. When you open the service, the status is visible on the Service Information Panel. Users may find it helpful to review and approve an IFSP and all services in one sitting.
3 | 2024-06-17 | Training Resources | EI-Hub | Users suggested that future training sessions for municipal staff be separated into two categories: EIO/D and SC. | With the rescheduling of the EI-Hub launch date, additional training opportunities will be provided, including in-person sessions throughout the state. While the exact dates are still being finalized, stakeholders can expect these trainings to occur in Summer 2024. We appreciate the feedback from stakeholders regarding the training format and the EI-Hub Project team will take this into consideration when planning for these training events. Understanding the functions of different user roles is important when adopting a new system. EIO/Ds and SCs do need to work together in the system and pass information back and forth. By understanding each other's roles, EIO/Ds and SCs can work together more effectively to support the child's progress through the Early Intervention Program. While in some counties these roles are held by different individuals, there are some counties where one person holds both the EIO/D and SC roles. When developing statewide training, we create content to accommodate local administrative models.
4 | 2024-06-12 | Child Demographics | Case Management | Users asked how address and telephone number history is tracked in the EI-Hub. | Address and telephone history is tracked in the EI-Hub. Address information is captured in both the Child and Family tabs. When entering a new address for a child or family member, ensure the previous address is end-dated before inputting the new one. The system will record the history of address changes in a grid. In the Family tab, you can add multiple telephone numbers. Use the notes section to indicate which numbers are current and provide any additional details, such as preferred contact times. See the Family Member / Family Base job aid for more information.
4 | 2024-06-03 | User Roles | Case Management | Users noted that the EIO/D role should have the ability to create Multidisciplinary Evaluation service authorizations. | Several municipal user roles, including the EIO/D role, have the capability to add a Multidisciplinary Evaluation (MDE) service authorization (SA) in the EI-Hub. The service authorization for a MDE is entered in the Eval tab on the Evaluation Information panel. For detailed information on how to enter MDEs in the EI-Hub, please refer to the training materials in the “Applicable Resources” column.
1 | 2024-06-03 | Service Authorizations | Case Management | Users suggest enhancing the service detail information when prompted to accept an assignment. | When a child is referred to a provider for services, the provider will receive a notification on their Children Assigned to Caseload dashboard. An "accept assignment" option will appear in the action column. Upon selecting this button, a pop-up will display additional information, including the type of service and the start and end dates. The frequency and duration of the service will only be visible after the user accepts the assignment and accesses the child's record. The system is intended to complement, not replace, direct communication between municipal and provider staff. While the system provides the above information, it is best practice for the service coordinator to confirm the provider's capacity to serve the child before assigning them. Additionally, if the provider needs more information, they can contact the service coordinator before accepting the assignment.
4 | 2024-05-24 | Billing & Claiming | EI-Hub | Users questioned if they need to include the waiver type and any CPT modifiers in an 837 file | The EI-Hub will automatically generate a waiver if the services added to an IFSP meet the criteria for a waiver. Users do not have to add the waiver type to an 837P file. If a claim violates a billing rule, the system will look to see if there is an approved waiver. If there is an approved waiver, the claim will pass validations. If there is not an approved waiver, the claim will get rejected. CPT modifiers are also applied on the backend, when appropriate. Users do not need to add modifiers to their 837P file.
4 | 2024-05-24 | Service Authorizations | Case Management | Users questioned if the UniversalProvNY user role has permissions to add a rendering provider to accepted services. | The UniversalProvNY user role has permissions to add therapist assignments in the EI-Hub. Users with this role can accept assignments on behalf of their agency and designate a therapist (rendering provider or evaluator) to the accepted service. To assign therapists, navigate to the 'Therapist Assignment' panel for services linked to an IFSP and the 'Evaluator Assignment' panel for evaluations.
4 | 2024-05-24 | Billing & Claiming | Case Management | Users are seeking clarification on the notification process if the ‘Scripts, Orders, Recommendations, and Referral’ panel is incomplete, leading to claim rejection. | If this panel is left incomplete when submitting the claim, users will receive notifications during the claim validation process. For 837 users, notification will be provided in the 277-response file. EI-Hub Service Logging users will find the claim in the ‘Unbilled’ report located under the Attendance menu. Please note, if this issue affects 10 claims under one service authorization, users will only have to submit the information in the ‘Scripts, Orders, Recommendations, and Referral’ panel once and it will apply to all claims.
4 | 2024-05-24 | Transition | Case Management | Users noted that the child’s third birthday is not included in the IFSP tab. | While the child's third birthday isn't directly displayed on this tab, the system includes logic to prevent the creation of an IFSP beyond this point. Users will encounter an error if they input a date extending beyond the child's third birthday, unless the child still qualifies for Early Intervention (EI) services under the CPSE. In the Transition tab, completion of the Part B eligibility panel, specifically the following fields: 1) Was the child determined eligible by CPSE and 2) If yes, the planned start date of 4410 will enable entry of an IFSP beyond the child’s third birthday. It is good practice to write down the child’s date of birth when working in their record.
3 | 2024-05-24 | Error Messages | Case Management | Users suggested enhancements to how error messages are displayed. | As we continue to test the system, we will be documenting opportunities to improve consistency of the error messages, where the messages populate on the screen, including consideration for where the user is on the screen when the error message populates. Error messages often appear at the top of the panel. Users should scroll to the top of the screen after submitting to view any potential error messages. Users will become more familiar with the information required in the system through consistent practice and utilization. This feedback has been shared with the development team for consideration as a future enhancement to the EI-Hub.
4 | 2024-04-29 | IFSP | Case Management | Users are asking why they are unable to update the IFSP outcomes once the IFSP is approved | IFSP outcomes are established during the IFSP meeting, collaboratively developed and approved by the parent/guardian. The EI-Hub is functioning as expected, any changes to these outcomes require consent from the parent/guardian and result in an amendment of the IFSP.
4 | 2024-04-29 | Service Authorizations | Case Management | Users expressed that the ‘Service Location’ panel seems unnecessary for service authorizations regarding service coordination. | The ‘Service Location’ panel is mandatory for all service authorizations. For service coordination, selecting the option for ‘caregiver’s home’ is recommended. Additionally, on this panel users are required to check the box indicating whether the service is being delivered in the child’s natural environment. For service coordination, selecting the option for ‘yes’ is recommended.
1 | 2024-04-29 | Transition | Case Management | Users provided suggestions for renaming the forms within the Transition tab and reorganizing the panels. | We thank you for sharing your feedback. We have shared this feedback with the project team for consideration as a future system enhancement around optimizing the Transitions tab.
4 | 2024-04-29 | Referrals | Case Management | Users had questions about how referrals are entered if a child’s record is reopened. | After a child has left the EIP their record will display in one of two different statuses: Closed or Exited. An EIP child record will close automatically after 5 years and 8 months of age. An At-Risk child record will close automatically after 36 months of age. When a child is exited from EIP, the child’s record is locked from editing; however, the child’s record may be reactivated and re-opened by the EIO, EIO/D, or County Data Entry for modification, such as a re-referral. When you reactivate and re-open a child’s record, your need to add the new referral information using the ‘Referral type’ of re-referral. The EI-Hub will track the 45-day timeline from referral to Initial IFSP. This metric can be monitored from the IFSP Dashboard using the “Children awaiting IFSP (45 day timeline)” alert option. In cases where the child’s record was exited and reopened, the 45-day timeline will be based on the re-referral date. Resources: Referral job aid
4 | 2024-04-29 | User Roles | Case Management | Users have shared that having multiple user roles make it more difficult to complete some of the required program functions. Things like generating a service authorization now require more than one role. | The separation of the roles and the ability for users to have multiple roles is a system feature that allows for flexibility for approved providers and municipalities across the state where program responsibilities and system access needs vary a great deal. Another benefit of the user role structure in the EI-Hub is that municipalities and agencies have autonomy in deciding what roles are appropriate for their staff and assigning those roles without Help Desk or Bureau support. Toggling between roles is something system users may find challenging now but over time will become less difficult as we all learn how to most efficiently use the EI-Hub. Thank you for this suggestion. We have shared this feedback with the project team for consideration as a future system enhancement.
3 | 2024-04-17 | Sandbox Functionality | EI-Hub Sandbox | Users expressed concerns that the system times out and they encountered slowness while navigating within the system. | The Sandbox is a testing environment. Development prioritizes optimizing performance for the live version of the system over the Sandbox. At the EI-Hub system launch, users can expect a different timeout experience compared to the Sandbox. Additionally, Development continuously works on enhancing the system's speed and ensure the system is performing its best.
4 | 2024-04-17 | Training Resources | EI-Hub | Counties have expressed concerns about providers reaching out to them for training assistance. | Counties are not responsible for training providers on the new system. Should providers seek support from the counties, they should be directed to the PCG Call Center for assistance. The PCG Call Center can be reached at 866-315-3747 or via email at nyeitraining@pcgus.com. Additionally, there are many resources available on the Learning Management System (LMS) to support users in learning the EI-Hub. Visit the LMS to view available job aids, e-learning modules, previously recorded webinars and more. If you are looking to see what resources are available on a specific topic area, please reference the LMS Item Index.
4 | 2024-04-17 | Child Demographics | Case Management | Users suggested adding additional child demographics information to the “at-a-glance” panel. | We understand that transitioning to a new system requires users to invest time and effort in familiarizing themselves with its features and adapting to new processes. While the child-at-a-glance panel may not encompass all the information available on the NYEIS main page, certain key details such as the child's name, date of birth, status, referral date, and IFSP end date are conveniently captured on the Children Assigned to Caseload dashboard. From the caseload dashboard, users can open the child’s record and find their address information on the child-at-a-glance panel and/or basic demographic information panel. Alternatively, users can access child information, including the details mentioned above and more, through the Child Detail report.
4 | 2024-04-08 | Sandbox Setup | EI-Hub Sandbox | Users expressed confusion that they are not seeing their entity’s information in the EI-Hub Sandbox | The Sandbox uses only fabricated (fake) data. This includes both child and provider data. The Sandbox is a practice environment where users can gain familiarity with the system. It is not setup to reflect the personal setup of your agency. Role Administrators have been assigned a test agency and they will able to view this assignment under the My Profile and Roles and Components section from the EI-Hub Sandbox Landing page. Role Administrators will only be able to assign user roles with the test agency they have been assigned. When working with a county in the Sandbox, you will want to communicate the name of the test agency you were assigned, so they can send children to you for practice.
4 | 2024-04-08 | Service Authorizations | Case Management | Users shared a suggestion, noting that they would like the service authorization information to stay visible after accepting an authorization. | Thank you for sharing your feedback. In the EI-Hub new service authorizations will appear on the user’s “Children Assigned to Caseload” dashboard, with an “accept assignment” button. After selecting this option, a pop-up window will appear with service type information and the option to accept or reject the assignment. It is important to note the child’s ID when the pop-up window appears so you can easily locate the child on your caseload dashboard after the assignment is accepted. Once submitted the pop-up window will disappear and the “accept assignment” button changes to an “edit” button, allowing the user access to that child’s record.
1 | 2024-04-08 | Service Authorizations | Case Management | Users expressed a desire to assign the rendering provider at the point when the service authorization is accepted. | Thank you for this suggestion! We have shared this suggestion with the project team for consideration as a future system enhancement.
4 | 2023-12-20 | Child Demographics | Case Management | Users suggested that having the ability to search for children by their date of birth would be beneficial. | The EI-Hub allows users to search for children by date of birth. Navigate to the Child Lookup section and in the 'Filter To' field, you can use the dropdown menu to select different search criteria, including ‘Children with a Date of Birth within the selected period’. Once you choose this option, additional fields will appear, enabling users to specify a particular date range for the birthdate. If you know the child’s exact birthdate, you can input the same date in the ‘Lookup Begin Date’ and ‘Lookup Thru Date’ fields.
4 | 2023-11-27 | IFSP | Case Management | Users state that the process to amend an IFSP is more complicated than compared to NYEIS. | Thank you for your valuable feedback. When a service coordinator needs to make an amendment to the IFSP, in the EI-Hub they will need to create a brand new IFSP. The EI-Hub allows them (and other authorized users) to copy/clone the existing IFSP which will populate with pre-existing data. The service coordinator then makes the amendment and is required to review all panels of the IFSP and update as needed, prior to submitting to the EIO/D for review. We understand the need to review and update all panels on an IFSP as part of an amendment, including the need to change dates and IFSP type, is a different process than currently exists in NYEIS. Re-submitting the entire IFSP provides the EIO/D with the opportunity to reassess the level of services and review the amended service in the context of the child’s total service plan. The pre-amended IFSP will be saved in the EI-Hub as part of the child's record and able to be reviewed, if needed. Please reference the IFSP Job Aid for more information on the amendment process. The IFSP amendment process in EI-Hub Sandbox reflects how the EI-Hub will operate when the system goes live. The concerns about the IFSP amendment process have been identified and documented to be considered for system revision after the EI-Hub launch.
3 | 2023-08-25 | User Roles | Case Management | Users reported the process for assigning EIO/Ds and ISCs is too fragmented, suggesting a new user role that can complete all functions involved in this process. | Thank you for your feedback. The EI-Hub allows users to have multiple user roles. User roles are set up in a hierarchical manner. The roles of MuniProgAllNY and UniversalProvNY have the capability to perform the majority of functions associated with other user roles. When assigning a child an EIO/D or ISC, users can navigate through the process utilizing these two user roles. The “Workflow Resource Guide” offers a comprehensive overview on how to guide a child through the EIP within the EI-Hub. This training resource informs users of the specific user roles capable of completing each step in the process. This resource is in its final stages of development and is expected to be posted to the LMS site soon. Available for review now on the LMS, is the Assigning EIO/Ds and Service Coordinators job aid.
3 | 2023-08-04 | IFSP | Case Management | Users reported issues with printing a completed IFSP where the printed version truncates the information entered into the system. | Thank you for reporting this issue. It has been shared with our development team to research and resolve. The project team is working to resolve the issue with printing an IFSP. We will update our response when a fix has been deployed.
4 | 2023-08-04 | User Roles | Case Management | Users have expressed that having the option for one universal role for counties to serve where one individual is the SC, EIOD, and data entry would save time and be less confusing by reducing the need to switch roles during a task. | Thank you for the feedback. The decision to build a system with the capability for users to have multiple user roles was made out of the desire to meet the broad needs of all of our counties and agencies. Shifting to this new model may require users to shift some of their business processes and their day to day processes to experience the full benefit of the multiple user role model. We anticipate that as users become more experienced in the EI-Hub the shifts between roles will become more natural and efficient and will not take as much time as it does for beginner users. Once your roles are set up you are able to switch case management roles from any screen in the EI-Hub case management module. To do this, select the "User Profiles" dropdown at the top right of the screen and select the appropriate role. Doing this will switch the user into that role and bring them to their EI-Hub case management homepage.
4 | 2023-07-14 | Training Resources | Learning Management System (LMS) | Users raised a concern regarding the accuracy of available job aids. | Job aids were developed alongside the system's development process. Draft versions of job aids are posted while there is still a possibility of system functionality changes. Once the system is officially launched, the job aids will align with the finalized functionality. We encourage Sandbox users to continue sharing their experience with available resources in the Learning Management System (LMS). We highly appreciate any feedback on how we can enhance the job aids to better meet the needs of users.
4 | 2023-07-07 | Child Demographics | Case Management | Users observed that Social Security Number (SSN) refusals are currently documented in the Child Info tab and expressed their interest in moving this information to the IFSP tab. | Thank you for providing us with valuable feedback. Your observation demonstrates your commitment to learning how to effectively utilize the EI-Hub. Social security numbers are required to be collected for eligible children, therefore it is recommended that local procedures related to the initial Individualized Family Service Plan (IFSP) meeting ensure that the Early Intervention Official (EIO) or Early Intervention Official Designee (EIO/D) provides parents with notice about the requirement to furnish social security numbers and collects the numbers at the IFSP meeting. The EIO cannot delegate the collection of social security information to service coordinators. The EIO or designee must obtain this information directly from parents. Currently, there are no plans to relocate this information, but we appreciate your feedback. To access BEI's guidance on obtaining SSNs, please reference the links provided.
3 | 2023-07-07 | At-Risk | Case Management | Users have reported that certain developmental surveillance tools commonly utilized in practice are currently not available in the At-Risk panels. | This is a known limitation in the Sandbox and is currently being addressed by the development team. The team is actively working on an update that will include the missing developmental surveillance tools in the At-Risk panels. Once the update is complete, the surveillance tools in the dropdown menu will be aligned with BEI’s guidance on assessment tools. As a reminder, there is an 'Other' option if the desired assessment tool is not available in the dropdown menu. The Project Team is exploring additional updates for the go-live version of the EI-Hub. For more information on recommended assessment tools, please reference the link provided.
3 | 2023-06-23 | Child Demographics | Case Management | Users expressed concerns regarding the inclusion of the middle name as an entry field within the referral panel, primarily due to the potential for data entry errors if users mistakenly enter the last name in this field. | While the middle name field is not mandatory in the referral panel, the last name field is required. If a user accidentally enters the last name in the middle name field and leaves the last name field blank, the user will get an error message. These measures aim to minimize the occurrence of data entry errors.
1 | 2023-06-23 | Child Demographics | Case Management | Users suggested reorganizing the options presented under the Child Info tab. | Thank you for this feedback! We have shared this suggestion with the project team as a recommendation for a future system enhancement.
4 | 2023-06-23 | Child Demographics | Case Management | Users suggested integrating the child's second language into the basic demographic information panel and removing the current panel dedicated to this information. | Thank you for providing this feedback! Currently, the child's second language is captured in a separate panel. This allows users to capture multiple secondary languages. For instructions on recording a child's second language in the EI-Hub, please refer to the Referrals job aid. We have also shared your suggestion with the project team to be considered as a possible future system enhancement.
4 | 2023-06-09 | Feedback Survey | EI-Hub | Users have expressed concerns regarding the word count limit of 100 words in the feedback survey. | Thank you for sharing your feedback with us. The Sandbox Feedback Form is designed to collect quick and anonymous insights specifically related to the EI-Hub and your experience with the Sandbox or associated training materials. However, if you have additional comments or feedback that cannot be adequately captured within the form, we encourage you to reach out directly to the EI-Hub Project team at EIHub@health.ny.gov.
3 | 2023-06-09 | Waivers | EI-Hub | Users have expressed concerns regarding the updated billing waiver guidance and its impact on the management of waivers in the EI-Hub. | We appreciate your concern as we realize these scenarios do occur. Waivers need to be discussed and approved at the IFSP and services are provided in accordance with the IFSP document. Any billing limitations that require a waiver should be addressed at that point. Should there be a subsequent child need or anticipated excess of service frequency (e.g., make up session) that would result in a billing violation, the provider should submit through EI-Hub a waiver request to the EIO/D no later than the anticipated service delivery date. If there are any issues, the provider should contact the municipality with more information regarding the waiver request. To view BEI’s guidance on waivers, please reference the provided resource.
3 | 2023-06-05 | IFSP | Case Management | User expressed concern about their agency not receiving their assignment for Early Intervention (EI) services attached to an IFSP. | The process begins when the Service Coordinator completes and submits the IFSP and Service Authorization(s) (SA) for EI services. Subsequently, the child appears on the EIO/D's IFSP Alert dashboard, under the alert type "IFSP submitted for review”. The EIO/D then reviews the IFSP and SAs, making a decision to either approve or reject them. Both the SAs and the IFSP must be approved by the EIO/D before the assigned agency receives notice of their assignment. The agency would then have to look in the Universal Provider All role on their “Child Assigned to Caseload” dashboard in order to view and accept the service assignment For more information on completing IFSPs in the EI-Hub, please refer to the training resources accessible on the Learning Management System (LMS). Additionally, stay tuned for the release of the Workflow Resource Guide, which will provide a comprehensive overview of the process flow in Case Management.
3 | 2023-06-02 | Service Authorizations | Case Management | User expressed concern about their agency not receiving their assignment for Early Intervention (EI) services attached to an IFSP. | The EI-Hub ensures that agencies do not receive assignments for Early Intervention (EI) services until the IFSP has been approved, thus preventing the initiation of services based on a non-approved IFSP. The process begins when the Service Coordinator completes and submits the IFSP and Service Authorization(s) (SA) for EI services. Subsequently, the child appears on the EIO/D's IFSP Alert dashboard, under the alert type "IFSP submitted for review”. The EIO/D then reviews the IFSP and SAs, making a decision to either approve or reject them. Both the SAs and the IFSP must be approved by the EIO/D before the assigned agency receives notice of their assignment. The agency would then have to look in the Universal Provider All role on their “Child Assigned to Caseload” dashboard in order to view and accept the service assignment For more information on completing IFSPs in the EI-Hub, please refer to the training resources accessible on the Learning Management System (LMS). Additionally, stay tuned for the release of the Workflow Resource Guide, which will provide a comprehensive overview of the process flow in Case Management.
3 | 2023-05-24 | IFSP | Case Management | Users expressed a need for additional guidance on how to enter service authorizations on the IFSP in the EI-Hub. | The process for entering service authorizations on an IFSP is different in the EI-Hub than it was in NYEIS and will require a period of time for users to learn and become familiar with the new process. Section 8 of the IFSP Required Fields Infographic (available on LMS) covers the process and required fields for entering a service authorization and the Creating a Service Authorization Job Aid (available on LMS) covers the specifics of the data being entered into those fields. Additionally, there is an IFSP Job Aid that talks about how users may copy/clone an IFSP as a starting point for future IFSP amendments or new IFSPs which includes the copying of services and service authorizations from the original IFSP. The training team is currently developing an IFSP eLearning Module and will take this comment under advisement as content is created.
4 | 2023-05-24 | Assigning Service Providers | Case Management | Users reported not being able to assign an Initial Service Coordinator preventing them from being able to use the Sandbox. | Assigning an ISC in the EI-Hub represents a significant change for system users. The project team has recently made available a job aid titled "Assigning EIO/Ds and Service Coordinators" on the Learning Management System (LMS). This resource serves as a guide, leading users through the process of adding ISCs to a child's record using the Teams tab. Additionally, users can refer to the "Creating a Service Authorization" job aid for instructions on submitting the service authorization for initial service coordination.
4 | 2023-05-05 | Sandbox Setup | EI-Hub Sandbox | Users reported difficulties setting up user role accounts for their county/agency. | BEI and PCG acknowledge the challenges Role Administrators and general users experienced during the roll out of the Sandbox. After receiving feedback, the Sandbox Setup Infographic was developed to guide users through the required steps to setup their county/agency in the sandbox. In addition to training resources on LMS, the Help Desk team is a great resource if you are experiencing difficulties in gaining access or getting set up in the Sandbox. Remember, all users will need an Health Commerce System (HCS) account to assess the EI-Hub Sandbox environment. To become active in the Sandbox environment, Role Administrators will need to provision each user’s account. The term ‘provisioning’ describes the process of setting up the IT infrastructure of an account. To begin this process, participants will need to log into the EI-Hub Sandbox environment to create the pathway between the Health Commerce System (HCS) and sandbox environment.
4 | 2023-05-05 | Sandbox Functionality | Case Management | User reported an issue with accessing the Sandbox due to a password problem. | To access the EI-Hub Sandbox environment, you need to use your Health Commerce System (HCS) login credentials. If you experience a password error while attempting to log in, you can reset your password by following the instructions available on the HCS login page under the "Forgot Your User ID or Password" section. If you continue to experience login issues, please contact the PCG Help Desk.
3 | 2023-05-05 | Sandbox Functionality | Case Management | Users have expressed frustration about their inability to use the sandbox due to a lack of child cases. | The Sandbox was set up to closely mimic or mirror how the system will work in real life. In the Hub, Municipalities will be responsible for handling the input of all referrals into the Hub, and then assigning service coordinators to continue with the referral process, etc. We acknowledge that the initial launch of the Sandbox was difficult for users to access the system and municipalities did not have adequate time to work with providers and setting up cohorts as had been anticipated. Please know that we have been interacting with municipalities and providers to learn about the difficulties they have experienced and are continuing to engage with municipalities so that they in turn will be able to re-engage with providers.
4 | 2023-04-21 | General System Functionality | Case Management | Users expressed concern that the EIO/D does not receive notifications when an MDE or IFSP is submitted for approval. | The EI-Hub utilizes dashboards to track a child's progress throughout the EIP. Dashboards replace the inbox and work queues currently used in NYEIS. Dashboards are organized by the different phases of a child's lifecycle in the EIP and users, including EIO/Ds, will need to check them regularly to stay up-to-date on the progress of children assigned to their workload. Dashboards are also equipped with a convenient download feature that allows users to export data and create customizable reports in Excel.
4 | 2023-04-21 | Child Demographics | Case Management | Users questioned how to complete the race/ethnicity fields if a parent declines to provide this information. | The race and ethnicity fields must be completed in NYEIS and will need to captured in the EI-Hub, as this is a federal reporting requirement. If a family is uncomfortable answering the questions related to these fields, we suggest that as a last resort, the individual collecting the information make a best guess selection as to the child's race/ethnicity, should the parent or referral source refuse to answer the question. The data recorded in the EI-Hub at the time of referral can be changed at a later time if necessary. We recognize that at times it will be difficult to assign race and ethnicity accurately to a child, however, the assigned person should complete this task to the best of their ability with consistency and objectivity.
4 | 2023-04-21 | Billing & Claiming | EI Billing | Users questioned how Code 35 Medicaid placements will be handled in the EI-Hub. | There will be no changes in the processing of code 35 Medicaid placements in the EI-Hub system as the EI Billing module will be integrated into the system. Service Authorizations information will be taken from the EI-Hub Case Management module and used to facilitate code 35 Medicaid placements in the EI Billing module.
3 | 2023-04-21 | IFSP | Case Management | Users are uncertain about which time increments to select from the drop-down menu in the Service Delivery panel for EI services that are not covered by the available options. | Thank you for providing your feedback. In the EI-Hub, time increments are listed in 15-minute intervals in the dropdown menu, unlike in NYEIS where users can enter the time in a free text field. This feedback has been shared with both the EI-Hub Project Team and the Development Team for further review and consideration of a system update.
4 | 2023-04-14 | Training Resources | Case Management | Users expressed concerns that training resources focus primarily on agencies and do not speak to the role or actions of a sole proprieter/individual provider. | The EI-Hub and the associated training resources refer to providers of record as the "provider" and the rendering provider as a "therapist." Sole proprieters or approved individuals with an appendix 1 agreement will act in both of these roles in the EI-Hub. When training resources refer to agencies performing a specific task, this is often inclusive of approved individual providers where appropriate.Approved individual providers will have multiple users roles in the EI-Hub including the UniversalProvNY, InProviderNY, and RenderProvNY.
4 | 2023-04-14 | Evaluations | Case Management | Users have indicated that the number of steps needed to assign an evaluator and the need to switch between the EIO/D role and the ISC role to complete the assignment is cumbersome. | As with any change, adjusting to a new system is difficult. The EI-Hub Project Team acknowledges that the layout and structure of the EI-Hub is different than NYEIS. There are several instances where data will carry over into different panels throughout the system. The separation of the roles between the ISC and the EIO/D is a system feature that allows for flexibility for other areas of the state which may not have individuals that serve both in the EIO/D and the ISC role. The ability to switch roles is also beneficial for those rendering providers that at times may also serve as service coordinators.
4 | 2023-04-07 | General System Functionality | Case Management | Users expressed their concerns regarding the amount of data entry required, noting that the information stored in the EI-Hub is not considered as the official child record. | The EI-Hub enables users to print IFSPs for record-keeping purposes. The system also streamlines data entry by carrying over the entered information, thus minimizing data entry as you progress through the system. While EI-Hub will allow users to upload attachments, the functionality to upload files/attachments does not replace record-keeping requirements or change record-keeping responsibilities of early intervention program providers and municipalities. Providers must retain the child record, including attachments, in their records for at least the number of years required to meet Medicaid requirements and for additional years to comport with their respective professional practice acts.
3 | 2023-04-07 | Child Demographics | Case Management | User inquired how they can search for siblings and non-siblings (e.g. in foster care) in the system. | When searching for a child using the Child Lookup feature, users can choose to search by the guardian's name by selecting the 'Guardian Name' option under the 'Name lookup' field. (see screenshot) Thank you for your comment. Your feedback helped us identify an opportunity to improve the Child Lookup job aid by including instructions on how to use this search feature.
3 | 2023-04-07 | IFSP | Case Management | Users reported challenges with the system requirement that the "Company Assignment Panel" be completed in order to allow the "Service Location Panel" of the IFSP to be completed and saved. | Thank you for reporting this issue. The Bureau and the project team undestand that locations where services will be provided is determined by the IFSP team who may need to document that decision before a provider/company has been identified. We have shared this feedback with our development team to research solutions. We will share updates as they are available.
3 | 2023-04-07 | Training Resources | Case Management | Users expressed concerns about support leading up to and after the launch of the EI-Hub. Specific concerns about how sole proprietors would access support without colleagues in an office setting to help were raised. | The EI-Hub Training Team is working to develop resources that cover all of the major aspects of the EI-Hub system and to plan for live training sessions ahead of the launch of the system. Even with these training resources, with a new system (or even an old system) it is expected there will be challenges. The EI-Hub Help Desk is available now for Sandbox users and will continue to be a valuable resource to end users (including sole proprieters) when the system goes live.
3 | 2023-04-07 | Training Resources | Case Management | Users have expressed a desire for more training opportunities, such as in-person or interactive training sessions. | We appreciate stakeholders continuing to share their feedback with us. When developing the training plan, BEI and PCG considered a variety of different training options. It was determined that virtual training would offer the most accessible format, as in-person trainings pose many logistical barriers. The EI-Hub Project Team will continue to explore creative possibilities to provide training including additional live hands-on sessions, understanding the desire for increased learner engagement.
4 | 2023-03-31 | Evaluations | Case Management | Users have expressed that the process to assign evaluators in the EI-Hub Sandbox is difficult. | The assignment of evaluators may have been challenging given that the Sandbox is not reflecting the level of data that the go-live version of EI-Hub will have. The data available in the Sandbox is added by Sandbox participants. Some cohorts may not have created therapists/evaluators yet. The training team is developing resources to guide users through the evaluation process!
4 | 2023-03-13 | Adding Therapists | Case Management | Users reported difficulties when entering Therapists (SC, EIO/D, and Rendering Providers) into the Case Management component. Users also reported difficulties configuring user role accounts for Therapists. | The development team has made a system update to fix issues with creating therapist records in Case Management. The Adding Therapist Information Job Aid has been updated and posted to the LMS.
4 | 2023-03-13 | Assigning Service Providers | Case Management | When assigning an agency/therapist no information or providers are coming up in the search so we are unable to assign a provider. | Thank you for this feedback! The development team has resolved a bug in the system that was preventing the search from populating with approved providers. Users should now be able to search and assign approved providers within their cohort. Please keep in mind only the "approved providers" created for the purposes of the Sandbox will be available through the search. Additionally, the training team is developing resources to support end user in creating service authorizations and assigning providers so please be on the look out for more updates!
4 | 2023-03-13 | Assigning Service Providers | Case Management | Users reported that they cannot approve an IFSP or enter the authorized services without adding the provider first. | Thank you for this feedback! The development team has made changes to the EI-Hub based on this feedback so users will no longer have to enter a provider before the IFSP can be approved or before services can be entered.
3 | 2023-03-13 | Assigning Service Providers | Case Management | Users reported that it is difficult to determine if service coordinators are accepting/rejecting cases or if their managers accept/reject the assigned case in the EI-Hub. | The Hub allows the flexibility to complete this process both ways dependent upon the practice of the municipality or agency. Utilizing the available dashboards allows users to track child assignments. New fields are being added to the Teams Tab where the approved provider will accept the assignment and then assign the rendering SC. The "Children Needing Service Coordinator Dashboard" will inform provider managers and EIO/Ds of which children assigned to the provider require a service coordinator. The "Children Assigned to Your Caseload Dashboard" can be used for service coordinators to view their caseload and to accept/reject an assignment. In the event a service coordinator rejects an assignment, the child will be listed on the manager's "Children Needing Service Coordinator Dashboard".
1 | 2023-03-13 | Child Demographics | Case Management | Users suggested adding additional child demographics information to the “at-a-glance” panel. | Thank you! We have shared this feedback with the development team for consideration as a future enhancement to the EI-Hub.
3 | 2023-03-13 | Dashboards | Case Management | Users have reported issues regarding dashboard alerts and functionality. | Dashboards are currently under development. While dashboards are functioning, Sandbox users may notice changes to alert names, action buttons, and other dashboard features. Please note, all training resources will be updated to reflect the final state of dashboards, prior to the launch of the EI-Hub.
3 | 2023-03-13 | EI-Hub Launch Date | EI-Hub | Users have requested more information on when the EI-Hub system will go-live. | At this time there has not been a date announced but BEI has committed to providing approximately two months’ notice before the launch date.
3 | 2023-03-13 | EI-Hub Launch Date | EI-Hub | Users have expressed preferences for when the EI-Hub system should launch. | The project team is considering several factors in determining the new go-live date of the EI-Hub, including municipal and provider feedback. BEI has committed to providing approximately two months’ notice before the launch date.
4 | 2023-03-13 | Evaluations | Case Management | Users with the UniversalProvNY do not have permissions to update the evaluation results. | Thank you for this feedback! The development team has released an update to the system that now allows UniversalProvNY users to edit/enter evaluation results for evaluations performed by their agency.
4 | 2023-03-13 | Evaluations | Case Management | Users reported that when entering evaluation information, the "Diagnosis Date" and "Diagnosis Code" fields, which are both required fields, disappeared once the "Outcome" field was complete. | Thank you for alerting us to this issue! The development team has resolved the issue. Now when the evaluator enters information into the Outcome field, the Diagnosis Date and Diagnosis Code fields will continue to be visible. Please see screenshot for confirmation.
3 | 2023-03-13 | Evaluations | Case Management | Users suggested that a comment box be added when an evaluation is authorized so that information such as the parent's concerns, and when the IFSP meeting is scheduled can be communicated to the evaluator. | Thank you for this feedback! We are sharing this and other feedback about where comment fields may be added to the EI-Hub with the development team for consideration as a future enhancements to the EI-Hub. The EI-Hub does have the ability to provide the IFSP meeting time and date to participants on the IFSP Details Panel. More information can be found in the IFSP Job Aid.
3 | 2023-03-13 | Evaluations | Case Management | User have expressed confusion about which scores must be completed within the EI-Hub as part of the evaluation, specifically whether the field "Raw Score" is required. | Thank you for this feedback! We recognize that the "Raw Score" is currently a required field in the EI-Hub. At the moment, this field can be completed by entering "N/A" if this is not applicable to testing tool utilized and the development team will be making an update to the system to make "Raw Score" an optional field in a future version of the EI-Hub.
4 | 2023-03-13 | General System Functionality | Case Management | Users reported concerns with the EI-Hub's system layout (i.e. number of tabs). | The layout and structure of the EI-Hub is different than NYEIS and there will be a period of adjustment for users. Over time, system users will become familiar with the system, including where certain tasks and activities are completed, and what fields or panels are required and data entry time should improve as users learn the system.
1 | 2023-03-13 | Evaluations | Case Management | Users have recommended that there should be an MDE Summary space for evaluators to enter comments about the evaluation and space within the domain sections of the MDE to enter narrative comments about the evaluation. | Thank you, this feedback has been shared with the development team as a future enhancement to the EI-Hub Will consider for future enhancements to the system. In the meantime users may consider uploading a paper copy of comments to be attached to the child's record.
4 | 2023-03-13 | General System Functionality | Case Management | Users reported looking for areas in the system to write general comments about a child | Users can enter/view comments about the child, that may not be captured in other tab/panels, in the ‘Contact Log’ panel - found in the Family Info tab. (i.e. parent concerns are that may have been discussed at the initial meeting, but not at the point of referral) This panel is viewable to all users with access to the child’s record. This panel can be edited by the following user roles: ProvDataEntryNY, ISC/OSC NY, RenderProvNY, JrRenderProvNY, MuniDataEntryNY, EOI/D NY, and MuniProgAllNY
1 | 2023-03-13 | General System Functionality | Case Management | Users provided several examples of how the EI-Hub requires redundant information be entered. | As with any change, adjusting to a new system is difficult. The EI-Hub Project Team acknowledges that the layout and structure of the EI-Hub is different than NYEIS. There are several instances where data will carry over into different panels throughout the system which will become more apparent as users become familiar with the system.
1 | 2023-03-13 | General System Functionality | Provider Management | Users requested consideration for an automatic interface with the Office of Professions. | Thank you for the feedback! Integration with outside systems is not something we are able to do at this time. Users, including the Bureau's Provider Approval Unit will need to continue to manually search the Office of the Professions.
1 | 2023-03-13 | General System Functionality | Case Management | Users suggested that the EI-Hub should automatically move users to the next tab when they have completed or submitted the tab they are currently working on. | Thank you for this feedback! We have shared this recommendation with the development team for consideration as a future system enhancement.
2 | 2023-03-13 | General System Functionality | Case Management | Users reported that dates in the EI-Hub do not pre-populate based on BEI programmatic timelines and indicate having more dates pre-populate reduce manual data entry. | Thank you for this feedback! We have shared the recommendation with the project team for consideration as a future system enhancement. The EI-Hub does have some date validations to generate an error message when an entered date does not meet the guidelines outlined in the EIP. Pre-populated dates while efficient are sometimes inaccurate, especially in cases where data entry is occurring on a different date than service delivery. In considering enhancing the EI-Hub to include more auto-populated dates, each date field will be considered independently to balance easing data entry to preventing data inaccuracies that could occur through auto-population.
3 | 2023-03-13 | General System Functionality | Case Management | Users suggested a system enhancement that would prevent users from being re-directed back to the "Services Information" panel each time they complete another panel. | Thank you for this feedback! We have shared this suggestion with the project team as a recommendation for a future system enhancement.
4 | 2023-03-13 | General System Functionality | EI-Hub | User reported that the text in the EI-Hub system is too small and monotone to view. | The EI-Hub has been validated through an ADA compliance screening process and meets all ADA requirements.
1 | 2023-03-13 | General System Functionality | Case Management | Users suggested an enhancement for the data entry process, where check marks are added indicating that all data entry requirements have been met for a particular section. | Thank you for this feedback! We have shared this suggestion the project team as a recommendation for a future system enhancement.
1 | 2023-03-13 | IFSP | Case Management | Users suggested that combining screens, tabs, or panels required for IFSPs may streamline the process for entering IFSP. | Thank you for this feedback! We have shared this suggestion with the development team for consideration as a future system enhancement.
1 | 2023-03-13 | Referrals | Case Management | Users recommended that the EI-Hub referral process be enhanced by adding the ability to bulk load referrals with the use of an excel file upload. | Thank you for this feedback! We have shared this suggestion with the development team for consideration as a future system enhancement.
4 | 2023-03-13 | Referrals | Case Management | Users suggested that they should be able to populate the referral agency drop-down. | Thank you for this feedback! In the Sandbox version of the EI-Hub, selection of a referral agency is not required. However, at a minimum, users are required to enter the Referral Source First and Last Name in order to submit the referral.
3 | 2023-03-13 | Sandbox Functionality | Case Management | Users identified issues with understanding catchment areas, assigning agencies, and assigning rendering therapists to services in the Sandbox. | Sandbox is a practice only environment, the data set available is limited. Some issues related to assigning therapists were identified early on and have since been resolved. The EI-Hub allows approved providers to identify their catchment areas which will make them selectable by those municipalities. The training team has developed resources to support users in managing their profile and for searching for and selecting billing and rendering providers.
4 | 2023-03-13 | Sandbox Functionality | Case Management | Users reported not having any information in the tabs and panels of the EI-Hub Sandbox. | There was a limited number of children pre-loaded into the EI-Hub Sandbox environment. This information was limited to child demographics to support users in creating a child record and support learning from the beginning of a child's lifecycle in EI. Sandbox users are encouraged to enter additional children through the referral process in the Sandbox, keeping in mind this data should not be real child data that would violate confidentiality. Providers, even Universal Providers will not be able to see those children until they have been assigned to their caseload. Please work with your cohort/municipality to have cases assigned to you in the EI-Hub Sandbox.
4 | 2023-03-13 | Sandbox Functionality | EI-Hub Sandbox | Users shared desire for increased communication about the status of the Sandbox (i.e. system bugs, system changes, etc.) | The Feedback on the EI-Hub System log was developed in response to user feedback. Feedback from users is reviewed regularly by the EI-Hub Project Team and this log will be updated on a bi-weekly (every other week) basis. Users will be able to see what their peers are saying about the EI-Hub and what the EI-Hub's Project Team's response is to the feedback.
4 | 2023-03-13 | Service Authorizations | Case Management | Users identified an issue with the need to assign an agency/provider of record for all services before the IFSP could be approved. | Thank you for this feedback! The development team has fixed this issue so that a service can be included on an IFSP even if there is not an available provider of record for assignment. This allows us to continue to track capacity issues in the program and ensure children as assigned providers as they become available. Additionally, the EI-Hub has a dashboard available titled "Children with an IFSP with Services Missing an Agency" available to service coordinators and EIO/Ds to support tracking and resolving these gaps on a child's IFSP.
3 | 2023-03-13 | Service Authorizations | Case Management | Users have provided specific feedback on the service authorization process being confusing and a suggestion that adding a comment field under the parent address section would be helpful. | The service authorization process is very different in the EI-Hub than in NYEIS, the training team is developing resources to support users in the creation of service authorizations for different service types. Some actions within the Hub require that steps be completed in a specific order and as the user becomes familiar with the System, they will learn the correct order of these steps. The Hub does allow users to enter different parent addresses to different parents. The suggestion for a comment box below the parent address field has been referred to the development team for consideration in future system enhancements.
1 | 2023-03-13 | Service Authorizations | Case Management | Users suggested that service authorizations should be automatically generated by the EI-Hub system. | Thank you for this feedback! This has been shared with the project team as a recommendation for a future system enhancement. We understand that manually entering service authorizations requires a significant amount of data entry. After the first IFSP has been created, service authorizations associated with that IFSP can be selected and cloned for subsequent IFSPs, if appropriate.
4 | 2023-03-13 | Therapist Information | Provider Management | Users have asked if they will be able to update rendering provider’s professional license information in the EI-Hub (i.e. expiration date). | Users with a UniversalProvNY, InProviderNY, or ProvDataEntryNY user role can update Therapist (rendering providers) licensure information in the EI-Hub.
3 | 2023-03-13 | Training Resources | Case Management | Users expressed that step by step guides and training are needed to help people learn the EI-Hub. | PCG and BEI are working to provide multiple resources to support users in all aspects of the EI-Hub and moving a child through the system. Since resources are being developed at the same time that the system is being finalized, not all resources may be available. Please check the LMS index as an up to date inventory of what training material on the LMS and let us know through the Sandbox Feedback Form if there are resources needed on a specific topic.
4 | 2023-03-13 | Transition | Case Management | User commented on Transition Panels "Part B Program Form A Part 1B" and "Transition Plan Non Part B program Form B Part 1B" being discontinued and added back. | IFSP Transition Plan Form A and Form B are forms that were designed to be aids to the service coordinator as they assist the family through the transition process. These forms were never discontinued by BEI. The Hub provides these and other forms under the tab "Documents" for the users' convenience. These panels in the EI-Hub are available to assist users in stepping through the transition process but are not required panels.
3 | 2023-03-13 | User Roles | Case Management | Users reported that it is not always clear what tasks or functions can be completed by whom (or what user role) in the EI-Hub. | The EI-Hub users roles have been developed to align system functions and user tasks with program roles and duties. A limitation of NYEIS was that users were only able to have one user role which resulted in many, very customized roles to meet individual needs. Users are now able to have multiple roles to allow them to complete system tasks associated with the user's various early intervention responsibilities. The training team is continuing to develop resources to support system users in identifying the appropriate user roles for them in the EI-Hub and understand what they are able to do while in each role.
Adding Therapist Information Job Aid
EI-Hub User Role Crosswalk
Dashboards Infographic
EI-Hub Workflow Resource Guide
Creating Service Authorizations Job Aid
Evaluations Infographic
Evaluations Job Aid
Provider Lookup Job Aid
Therapist Lookup Job Aid
Sandbox Facilitation Guide
Referrals eLearning Module
Referrals Job Aid
Child Look Up Job Aid
EI-Hub Workflow Resource Guide
EI-Hub User Roles Crosswalk
Case Management User Guide Unit 8
Assigning an EIO/D and Service Coordinators Job Aid
EI-Hub Workflow Guide Resource
Assigning EIO/Ds and Service Coordinators Job Aid
Dashboards Infographic
IFSP Job Aid
Case Management User Guide Unit 8
IFSP Job Aid
IFSP Required Fields Infographic
Creating a Service Authorizations Job Aid
Evaluations Job Aid
Referrals eLearning Module
Referrals Job Aid
Transition Update: Referrals
Sandbox Setup Infographic
Evaluations Job Aid
Evaluations Infographic
LMS Index
EI-Hub Workflow Resource Guide
Evaluations Job Aid
Evaluations Infographic
Case Management User Role Job Aid
Creating Service Authorizations Job Aid
Creating Service Authorizations Job Aid
Provider Search Job Aid
Therapist Search Job Aid
Provider Amendments, reapprovals, and minor changes job aid
Case Management User Roles Job Aid
Case Management User Guide Unit 8
Hub Club Issue 24
User Role Configuration Job Aid
Referrals eLearning Module
Referral Job Aid
Transition Update: Referrals
LMS Index
EI-Hub User Access Admin Guide
EI-Hub Transition Resource Lists
EI-Hub Workflow Resource Guide
EI-Hub Workflow Resource Guide
Case Management User Guide - Unit 7 Dashboards
Dashboards Infographic
Case Management User Guide - Unit 7 Dashboards
Provisioning General Users in the EI-Hub Sandbox
EI-Hub Workflow Resource Guide
IFSP Job Aid
IFSP Required Fields Infographic
EI-Hub Workflow Resource Guide
EI-Hub Workflow Resource Guide
EI-Hub Waivers Infographic
Memo 94-2 Wavier of Billing Limitations 2023
BEI Guidance on SSN
EIP List of Developmental Assessment Instruments, May 2023
EI-Hub User Role Crosswalk
Case Management User Roles Job Aid
Case Management User Guide Unit 8
EI-Hub Workflow Resource Guide
EI-Hub Workflow Resource Guide
Assigning an EIO/D and Service Coordinators Job Aid
IFSP Job Aid
Role Administrator Request form
Sandbox Setup Infographic
EI-Hub Workflow Resource Guide
LMS Index
EI-Hub Child Reports Job Aid
Case Management User Guide - Unit 7 Dashboards
Creating a Service Authorizations for General Services Job Aid
OPRA Guidance
OPRA FAQs
CPT/HCPCS Codes Accepted in the EI-Hub
Create a Service Authorization Job Aid
Entering Evaluations Job Aid
Case Management User Guide - Unit 7 Dashboards
277CA Companion Guide
Transitions Job Aid
Case Management User Guide - Unit 7 Dashboards
Entering Evaluations Job Aid
EI-Hub Workflow Resource Guide
Entering Service Authorizations for
General Services
Early Intervention Program Regulations Section 69-4.26(b)
Workflow Resource Guide - IFSP section
LMS Item Index
Quick Start Guide - Role Administrators
Quick Start Guide - General Users
Entering Service Authorizations for
General Services
Entering Service Authorizations for
General Services
Assigning EIO/D and SC job aid
Communications packet
Workflow Resource Guide
Entering Service Authorizations for
General Services
Create/Edit a Service Log job aid
Enter Insurance Information job aid
Case Management User Guide - Unit 7 Dashboards
Creating a Service Authorizations for ISC Job Aid

## Sheet2 (hidden)
Status Descriptions
4 | Completed / Implemented
3 | In Progress
2 | Delayed / Discontinued
1 | Not Started